|  | # Arrowhead Head Start Recruitment Plan ## Program Year 2026/2027 |  |
| --- | --- | --- |
| # Time Frame | # Strategy | # Responsible |
| # December | Update 2026-2027 enrollment application and prescreening forms (if necessary). Submit necessary enrollment policies for review and approval by Policy Council. Create recruitment materials (postcards, children’s books, flyers, etc.). | ERSEA & Business Analyst & Compliance Administrator (BACA) ERSEA Manager/Policy Council ERSEA Manager |
| # January | Conduct recruitment training for Family Service Staff ensuring all program options are promoted (Center and Home Base). Develop plans of action on places and times where Family Service Staff will strategically plan their recruitment efforts. Set schedules for attendance at WIC clinics MFIP/SNAP participation lists for informational mailings. Inform other service providers regarding the kick-off of Head Start Recruitment season. Current HS/EHS wait lists for staff to contact for new applications. Begin social media messaging for Head Start recruitment. Begin print media message for Head Start recruitment. | ERSEA Manager ERSEA Manager # FSS # ERSEA Manager ERSEA Manager/Other staff as part of community groups ERSEA Manager ERSEA Manager/FSS ERSEA Manager |
| # February | Complete community assessment of early childhood programs available in our communities. Coordinate mailing through school districts and run ads in school newspapers. Put up recruitment posters and distribute fliers and brochures. Target lower-income areas and services. Promote Early Childhood Literacy and Head Start recruitment with flyers and books in service area. Work with Energy Assistance Program to coordinate target mailings for families with children under 5. Continue to promote Head Start through public television and other media as budgetarily possible. Begin OutFront Media on-line campaign, if affordable Reach out to local HRA programs to promote mailers to their residents. | ERSEA Manager FSS/ERSEA Manager FSS FSS ERSEA Manager ERSEA Manager/FSS/HV ERSEA Manager ERSEA Manager |
| # March (and ongoing thereafter) April/May April | Place ads in community newspapers in areas where recruitment is low (as affordable). Attend School Open Houses for families to promote all Head Start Services. (As allowed/appropriate) Work with Disabilities and Mental Health Managers to cover area services for children with special needs such as LEAs and Range Mental Health. Target currently underserved areas to determine need for services (Newspapers, Referral Sources, mailings, etc.) Work with Disabilities and Mental Health Manager to determine priority of children to be accepted. Begin early enrollment of repeating children and continue early enrollments as possible. Report to IDT and Policy Council on recruitment progress (on-going). | ERSEA Manager FSS ERSEA Manager/FSS/Education Staff ERSEA Manager/DMH Mgr ERSEA Manager FSS/HV ERSEA Manager/DMH Mgr ERSEA Manager/DMH Mgr ERSEA Manager |
| # May # June | Final Mass acceptance. Policy Council approval for 2026/2027 sites. Mail acceptance packets to families Mail waiting list letters to families including other area options for early childhood programs. Work with EHS Mgr and Home Base Educators to identify children for 2026-2027 program year. Family service staff participate in community events to promote Head Start and solicit applications. At least 3 per month for FSS. | ERSEA/DMHM ERSEA Manager/PC ERSEA Manager/Program Support ERSEA Manager/Program Support ERSEA Manager/ EHS Mgr ERSEA Manager/EHS Manager, FSS, EHS HV |
| # Ongoing | Enrollment of new children as needed. Work with EHS Manager to maintain full enrollment of Early Head Start and Child Care programs throughout the year, with mass acceptance of new incoming applicants in July. Recruitment and public relations in community events throughout the year. (e.g. fairs, mall events, parades, homeless outreach events, National Night Out, etc.) Coordinate with local newspapers and television stations to promote public awareness of Arrowhead Head Start. Coordinate and collaborate with other Early Childhood programs to ensure service is provided to children and potential partnerships. | ERSEA Manager ERSEA Manager, EHS HV, FSS EHS Program Manager ERSEA Manager HS Staff ERSEA Manager HS Director HS Managers Community Early Childhood Programs |

Approved by Policy Council on _12-10-25__

DMH Mgr – Disabilities/Mental Health Manager		PC – Policy Council			FSS – Family Support Specialist

EHS HV – Early Head Start Home Visitors		HV – All Home Visitors (PSHB)	IDT – Management Team

ERSEA Manager – Family Services, ERSEA and Community Relations Manager